## Sheet1
Tracker Database - Project Schedule
Team Name: | Team 5
| Project Manager: |  |  | James Hare
| Project Start Date: |  |  | 2018-01-15 | time axis 2018-01-15 to 2018-03-12
| Display Week: |  |  | 1 |  |  |  |  | 2018-01-15: Week 1; 2018-01-22: Week 2; 2018-01-29: Week 3; 2018-02-05: Week 4; 2018-02-12: Week 5; 2018-02-19: Week 6; 2018-02-26: Week 7; 2018-03-05: Week 8
[9 empty] | 2018-01-15 | [6 empty] | 2018-01-22 | [6 empty] | 2018-01-29 | [6 empty] | 2018-02-05 | [6 empty] | 2018-02-12 | [6 empty] | 2018-02-19 | [6 empty] | 2018-02-26 | [6 empty] | 2018-03-05
WBS | Task | Lead | Prede cessor | Start | End | Cal. Days | % Done | Work Days | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
1 | Phase 1 - Kickoff | Deadline Jan 24
1.1 | Project schedule and meeting minutes | James Hare |  | 2018-01-15 | 2018-01-18 | 4 | 100% | 4
1.2 | Compile questions for meeting | Team |  | 2018-01-18 | 2018-01-23 | 6 | 100% | 4
1.3 | Requirements document | Daniel Velasquez/ Richard Kimsey |  | 2018-01-22 | 2018-01-24 | 3 | 100% | 3
1.4 | Complete Issues Log | Javier Martinez |  | 2018-01-22 | 2018-01-24 | 3 | 100% | 3
1.5 | Complete slides for meeting | James Hare |  | 2018-01-22 | 2018-01-24 | 3 | 100% | 3
1.6 | Peer Reviews | Team |  | 2018-01-22 | 2018-01-24 | 3 | 100% | 3
2 | Phase 2 - Database Design | Deadline Feb 19
2.1 | Project Plan and Schedule | James Hare |  | 2018-01-22 | 2018-01-24 | 3 | 100% | 3
2.2 | Update Project Document for Sprint | Daniel Velasquez/ Richard Kimsey |  | 2018-01-25 | 2018-01-29 | 5 | 100% | 3
2.3 | Update Issues Log | Javier Martinez |  | 2018-01-25 | 2018-01-29 | 5 | 100% | 3
2.4 | Meet with Client at 15:15 | Team |  | 2018-01-30 | 2018-01-30 | 0 | 100% | 1
2.5 | Respond to feedback from client | Team |  | 2018-01-30 | 2018-02-04 | 6 | 100% | 4
2.6 | Complete slides for class presentation | Team |  | 2018-02-02 | 2018-02-05 | 4 | 100% | 2
2.7 | Database Deisgn Period | Team |  | 2018-02-05 | 2018-02-13 | 9 | 100% | 7
2.8 | Update Project Document for Sprint | Daniel Velasquez/ Richard Kimsey |  | 2018-02-14 | 2018-02-16 | 3 | 100% | 3
2.9 | Complete Issues Log | Javier Martinez |  | 2018-02-14 | 2018-02-16 | 3 | 100% | 3
2.10 | Complete slides for meeting | James Hare |  | 2018-02-14 | 2018-02-16 | 3 | 100% | 3
2.11 | Peer Reviews | Team |  | 2018-02-16 | 2018-02-18 | 3 | 100% | 1
2.12 | Team Meeting with Prof. Hare | Team |  | 2018-02-19 | 2018-02-19 | 1 | 100% | 1
3 | Phase 3 - Implementation | Deadline Mar 19
3.1 | Project Plan and Schedule | James Hare |  | 2018-02-19 | 2018-02-21 | 3 | 100% | 3
3.2 | Contingency Plan | James Hare |  | 2018-02-22 | 2018-02-26 | 5 | 100% | 3
3.3.0 | Database Modification Period | Team |  | 2018-02-26 | 2018-03-16 | 19 | 100% | 15
3.3.1 | Modify database login access | Richard Kimsey |  | 2018-02-26 | 2018-02-28 | 3 | 100% | 3
3.3.2 | Remove search by customer functionality | Daniel Velasquez |  | 2018-02-28 | 2018-03-01 | 2 | 100% | 2
3.3.3 | Make audit table for accountability | Javier Martinez |  | 2018-03-01 | 2018-03-02 | 2 | 100% | 2
3.3.4 | Add triggers to delete functionality to populate audit tables | Richard Kimsey |  | 2018-03-02 | 2018-03-06 | 5 | 100% | 3
3.3.5.1 | Add restrictions on user input on the target width and target height fields | James Hare |  | 2018-03-05 | 2018-03-07 | 3 | 100% | 3
3.3.5.2 | Standardize all measurements into either centimeters or inches | James Hare |  | 2018-03-07 | 2018-03-08 | 2 | 100% | 2
3.3.6 | Provide an easy way to globally change background logo | Javier Martinez |  | 2018-03-08 | 2018-03-09 | 2 | 100% | 2
3.3.7 | Consolidate all instructions into one table dependent on an index table | Daniel Velasquez |  | 2018-03-09 | 2018-03-13 | 5 | 100% | 3
3.3.8 | Change report form layout | Richard Kimsey |  | 2018-03-13 | 2018-03-14 | 2 | 100% | 2
3.4 | Update Project Document for Sprint | James Hare |  | 2018-03-14 | 2018-03-16 | 3 | 100% | 3
3.5 | Complete Issues Log | Javier Martinez |  | 2018-03-14 | 2018-03-16 | 3 | 100% | 3
3.6 | Complete slides for meeting | Team |  | 2018-03-14 | 2018-03-16 | 3 | 100% | 3
3.7 | Peer Reviews | Team |  | 2018-03-16 | 2018-03-18 | 3 | 100% | 1
3.8 | Team Meeting with Prof. Hare | Team |  | 2018-03-19 | 2018-03-19 | 1 | 100% | 1
3.9 | Team Meeting with Prof. Hare | Team |  | 2018-02-19 | 2018-02-19 | 1 | 100% | 1
3.10
|  |  |  | 2018-01-15 | 2018-01-15 | 1 | 0% | 1
|  |  |  | 2018-01-16 | 2018-01-16 | 1 | 0% | 1
|  |  |  | 2018-01-17 | 2018-01-17 | 1 | 0% | 1
|  |  |  | 2018-01-18 | 2018-01-18 | 1 | 0% | 1
|  |  |  | 2015-04-01 | 2015-04-17 | 17 |  | 13
|  |  |  | 2015-04-01 | 2015-04-01 | 1 |  | 1
|  |  |  | 2015-04-01 | 2015-04-03 | 3 |  | 3
|  |  |  | 2015-04-04 | 2015-04-10 | 7 |  | 5
|  |  |  | 2015-04-13 | 2015-04-17 | 5 |  | 5
4 | Phase 4 - Testing | Deadline Apr 16
4.1 | Project Plan and Schedule | James Hare |  | 2018-03-19 | 2018-03-21 | 3 | 100% | 3 | bar: 2018-01-22 M to 2018-01-22 W
4.2 | Peer review each others tasks | Richard Kimsey/ Daniel Velasquez |  | 2018-03-21 | 2018-03-27 | 7 | 100% | 5 | bar: 2018-01-22 T to 2018-01-29 M
4.3 | Complete poster & demo for Tech Symposium | Javier Martinez/ James Hare |  | 2018-03-26 | 2018-04-01 | 7 | 100% | 5 | bar: 2018-01-22 T to 2018-01-29 M
4.4 | Devise test plan | James Hare |  | 2018-04-02 | 2018-04-03 | 2 | 100% | 2 | bar: 2018-01-29 T
4.5 | Devise tests for solution | Richard Kimsey/ Daniel Velasquez |  | 2018-04-02 | 2018-04-05 | 4 | 100% | 4 | bar: 2018-01-29 T to 2018-01-29 S
4.6 | Conduct written tests | Javier Martinez/ James Hare |  | 2018-04-06 | 2018-04-10 | 5 | 100% | 3 | bar: 2018-01-29 F to 2018-02-05 M
4.7 | Update Project Document for Sprint | James Hare |  | 2018-04-10 | 2018-04-13 | 4 | 100% | 4 | bar: 2018-02-05 M to 2018-02-12 T
4.8 | Complete Issues Log | Javier Martinez |  | 2018-04-10 | 2018-04-13 | 4 | 100% | 4 | bar: 2018-02-12 W to 2018-02-12 F
4.9 | Make sure project document is completed with links to supporting documentation | Team |  | 2018-04-13 | 2018-04-17 | 5 | 100% | 3 | bar: 2018-02-12 W to 2018-02-12 F
4.10 | Practise presentation for final presentation and technology symposium | Team |  | 2018-04-18 | 2018-04-18 | 1 | 100% | 1 | bar: 2018-02-12 W to 2018-02-12 F
4.11 | Final Presentation | Team |  | 2018-04-19 | 2018-04-19 | 1 | 100% | 1 | bar: 2018-02-12 W to 2018-02-12 F
4.12 | Technology Symposium | Team |  | 2018-04-20 | 2018-04-20 | 1 | 100% | 1 | bar: 2018-02-12 W to 2018-02-12 F
4.13 | Complete "Lessons Learned" document | Team |  | 2018-04-20 | 2018-04-23 | 4 | 100% | 2 | bar: 2018-02-12 W to 2018-02-12 F
4.14 | Peer Reviews | Team |  | 2018-04-23 | 2018-04-23 | 1 | 100% | 1 | bar: 2018-02-12 W to 2018-02-12 F
4.15 | Submit final project | Team |  | 2018-04-23 | 2018-04-23 | 1 | 100% | 1 | bar: 2018-02-12 F to 2018-02-12 S